## Mobile_Development
Inlooh - iOS/Android Mobile Application Design & Development
Technology: PhoneGap - Ionic Framework, JavaScript, HTML5/CSS3, MySQL
Module | Task | Hybrid Development | Resource
Time [Hrs.]
Application Design & Integration
App Design | Home Page Mock up Design |  | App Designer
Home Page modifications & finalization
Inner Pages Design (Main Templates)
Design Slicing | PSD Design to HTML5/CSS3 conversion Our Designers will convert finalized PSD Design to HTML5 pages along with CSS3 implementation. |  | PhoneGap Developer
Integration to PhoneGap Framework Once the HTML5 pages would be ready, we would integrate them to PhoneGap framework during Development phase.
Application Development (Project Scope)
Splash Page | App Logo Show App logo with background Image. | 8
Note: Client needs to provide logo image to be inserted.
Keep Splash Page stayed for some time while loading an app and then take user to Login Page.
Note: App Language would be English for now.
User Sign up | New Users need to fill in the required information and get registered on app. Information would be | 25
- First Name - Last Name - Email Address - Phone Number
- Password - Confirm Password and submit details.
Functionality constraints & validations implementation
Upon submit, it will save user's data into DB using web services.
Send Welcome Email to User
Link Bank Account | Ask User to enter US Bank Account Number and link it with his/her account
Create User's Account & Link Account on Dwolla Platform via API
Verify Bank Account via Dwolla API
Recommendation: We recommend you to use Dwolla API (www.dwolla.com) which allows peer to peer money transfer using APIs. We would use Dwolla API and allow users to transfer Gift Amounts between Sender & Recipient's Bank Accounts.
Note: Client needs to subscribe to Dwolla API and provide us the required details to be integrated.
User Login | User Login with Username/ Password Take User to Dashboard (Send a Gift) upon successful login.
Remember Me
Forget Password
User Login via Facebook
Send a Gift | Allow Users to send a Gift from here. | 40
Ask user to
- Gift Title
- Enter who the gift is to
- Enter who this gift is from
- Select Date you want to send gift
- Create a Video (up to 10 sec) Ability to record video via device camera (Front or Back) and confirm the same.
- Enter $ Amount
- Enter Recipient Details (Email Address or Phone Number)
- Enter Credit/ Debit Card Details to pay gift amount
Submit Details It will save details into DB using Web Services. App will make payment to Merchant account first.
Note: App will make payment to Merchant account first. Then Merchant needs to take care of making payment to recipient manually when there is withdraw request from recipient.
Show Thank You Message
Send Push and/or Email Notification to Recipient based on whether s/he is registered on App or not.
Note: In case of Text, It will populate a SMS with required details into Native App and user needs to send it via Send button on Native SMS app.
Transfer Money | Money Transfer Implementation via Dwolla API | 16
Functionality Our Developers would implement functions that will capture Sender's & Recipient's Dwolla accounts and make X USD transferred from Sender's to Recipient's Bank Account.
Initiate Bank Transfer when recipient views & accept the money.
Receive a Gift | Receive Push and/or Email/Text notification for Gift received click on it and it will come up with Gift Details | 22
Ask User to Sign in New Users needs to sign up first and then sign in to view the gift details.
Gift Details It shows Gift Details.
Play Gift Video
View Gift Amount & Accept the same
App will initiate & transfer the Money from Sender's Bank Account to Recipient's Bank Account once recipient accepts the same.
Menu | Navigation Menu Implementation Click on Menu and it will come up with menu items sliding from left to right. Click on any Menu Item and it will take user to specific page. | 16
Allow Users to view - About us - How it works - Contact Us - FAQs - Terms of Use, Privacy Policy & Security Policy
History | Allow Users to view all gifts received till now. | 8
List down Gifts by Date (Most to Least) Users can scroll down & up and view all Gifts received.
Click on any one and it will come up with selected Gift Details.
Total Hours |  | 135
Web Developer
Web Services
Web Services | Database Design & Set up
Our Developers will implement web services for all functionalities (as mentioned above) which will send & receive data between App & Server Database.
Total Hrs |  | 0
Notes
iPhone and Android Mobile application will use Portrait layout throughout the execution.
iOS application will support iPhone 5/5S/5C, iPhone 6/6s/6plus/7/7plus with OS versions 9 & 10.
Android application will support Mobile devices with resolutions 480 x 800, 720 x 1280, 1080 x 1920 Pixels with OS 4.x & 5.x versions.
This estimation does not consider Admin Panel development for now. Client needs to provide Cloud Server (with SSL certificate integration) to deploy the DB & Web Services.
This estimation is based on above explained features which is subject to change based on any change in features/functionality while in actual implementation.